## Bug Report
Category | Label
Bug ID | ID Number | Bug-01 | Bug-02 | Bug-03 | Bug-04 | Bug-05 | Bug-06 | Bug-07 | Bug-08 | Bug-09 | Bug-10 | Bug-11 | Bug-12 | Bug-13 | Bug-14 | Bug-15 | Bug-16 | Bug-17 | Bug-18 | Bug-19 | Bug-20 | Bug-21
| Title | First login no personal details displayed | personal information saving with a blank fields | State/Provice not switching | City/Town Field bug | Zip Code Field bug | Date of Birth Field bug | Name Field bug | Issue Date Field bug | Company Name Field bug | Job Title Field bug | From/To Work Experience Date bug | Deleting an Education entry bug | Deleting Multible Education entry bug | The ‘Major/Specialization’ field bug | The ‘Institution’ Field bug | The ‘Year’ field bug | The Year fied format bug | GPA/Score field bug | Start/End date fields bug | License Number field bug | The Issue/Expiry date field bug
| Reporter | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi
| Submit date | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025 | 16/08/2025
Bug overview | Summary | the system does not display the Personal Details screen upon the user’s first successful login. | The system save the personal information entry when the fields are blank | the State/Province field switches correctly between dropdown and text input when changing the country selection | the City/Town field accepts invalid inputs | The ZIP Code Field accepts invalid inputs | No appropriate error message.when entering invalid(Future)D.O.B e.g. 31/08/2025 | The name field accept invalid inputs e.g. Numbers, special characters | The issue date accepts a date after the current date issue date :31/08/2025 | The ‘Company Name’ accepts invalid inputs e.g. special charaters | The Job Title accepts invalid inputs e.g. Numbers and special characters | The Work Experience ‘From/To’ date fields accepts dates later than today (future dates). | An Education entry is not deleted , an error message displaye | Multiple Education entries are not deleted at once, an error message displayed | The ‘Major/Specialization’ field accepts invalid iputs e.g. Numbers and special characters | The ‘Institution’ field accepts invalid iputs e.g. Numbers and special characters | The ‘Year’ field accepts invalid inputs e.g.(alphabatical, special characters) | the Year field accepts un valid year format e.g." 1" | The "GPA/Score" field accepts invalid input e.g.(alphabatical, special characters) | The start/End date fields accepts dates later than today date (future dates). | The "license Number " field accepts invalid inputs " e.g.alphabetical and special characters" | The Issue/Expiry date fields accepts dates later than today e.g. (future dates)
| place | User Module-My Info | User Module-My Info-personal information | User Module-My Info-contact Details | User Module-My Info-contact Details | User Module-My Info-contact Details | User Module-My Info-Dependent | User Module-My Info-Dependent | User Module-My Info-Immigartion | User Module-My Info-Qualification- work experience | User Module-My Info-Qualification- work experience | User Module-My Info-Qualification- work experience | User Module-My Info-Qualification- Education | User Module-My Info-Qualification- Education | User Module-My Info-Qualification- Education | User Module-My Info-Qualification- Education | User Module-My Info-Qualification- Education | User Module-My Info-Qualification- Education | User Module-My Info-Qualification- Education | User Module-My Info-Qualification- Education | User Module-My Info-Qualification- License | User Module-My Info-Qualification- License
URL
| Screenshot | Screen shot 1 | Screenshot 2 | Screenshot 3 | Screenshot 4 | Screenshot 5 | Screenshot 6 | Screenshot 7 | Screenshot 8 | Screenshot 9 | Screenshot 10 | Screenshot 11 | Screenshot 12 | Screenshot 13 | Screenshot 14 | Screenshot 15 | Non-reproducible bug | Screenshot 17 | Screenshot 18 | Screenshot 19 | Screenshot 20 | Screenshot 21
Environment | Platform | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser | Web Browser
| Operating System | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10
| Browser | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome
Bug details | Steps to reproduce | 1- Log in with a valid user account account"first login" 2-click the"login"button 3- observe that page displayed | 1-locate "My Info""screen on the left panel 2-Navigate to "Contact information" 3-click on "Contact information" 4- intentionally leave all fields blank 5-click"save"button 6-observe the system response | 1-Locate My Info on the left panel 2-Navigate to Contact Information. 3-Click on Contact Information. 4-Select United States from the Country dropdown. 5-Observe the State/Province field format. 6-Change the Country selection to Palestine. 7-Observe the State/Province field format again. | 1-Locate My Info on the left panel 2-Navigate to Contact Information. 3-Click on City/town field 4-Enter invalid inputs 5- Observe the system response | 1- Navigate to the “contact Details” screen 2-locate the Zip/Postal Code 3- enter invalid inputs as the test data section 4- observe the system's response | 1- Navigate the"Depemndent " in the personal column 2-Enter the Name field and intentionally enter an invalid D.O.B 3- Click the "Save" button. 4- Observe the system's response | 1- Navigate to the dependent screen. 2- Enter an invalid Name as in test data 3- complete entering the required fields 4- click on "save"button 5- Observe the system's response | 1- Navigate to the immigartion screen. 2- Enter the invalid immigration issue date as in the input 3- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the Work Experience Section 3- click on "Add"button 4-Enter the invalid test data into "Company" field 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the Work Experience Section 3- click on "Add"button 4-Enter the invalid test data into "Job Title" field 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the Work Experience Section 3- click on "Add"button 4-Select a future date in the" From or To" field 5- Observe the system's response | 1- Navigate the"Qialification " in the personal column 2- Locate the education Section 3- click on the square checklist next to the desired "education " entry 4-click on"delete selected" button above 5- after the confirming messgae displayed click "yes,delete" 6-Observe the system's response | 1- Navigate the"Qialification " in the personal column 2- Locate the Education Section 3- click on multible square checklists next to the "education " entries 4-click on"delete selected" button above 5- after the confirming messgae displayed click "yes,delete" 6-Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the education Section 3- click on "Add"button 4-Enter the invalid test data into "Major/Specialization" field as specified in the Test Data 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the education Section 3- click on "Add"button 4-Enter the invalid test data into "Institution" field as specified in the Test Data 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the education Section 3- click on "Add"button 4-Enter the invalid test data into "Year" field as specified in the Test Data 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the education Section 3- click on "Add"button 4-Enter an invalid year format as provided in the test data 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the education section 3- click on "Add"button 4-Enter the invalid input as provided in the test data 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the Education Section 3- click on "Add"button 4-Select a future date in the" Start or End " date field 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the license Section 3- click on "Add"button 4-Enter the provided invalid test data into "license number" field 5- Observe the system's response | 1- Navigate the"Qualification" in the personal column 2- Locate the License Section 3- click on "Add"button 4-Select a future date in the" issue or Expiry " date field 5- Observe the system's response
| Expected result | The user should be successfully redirected to the personal details screen after the first login | The system should not display a successfully updated message when no changes have been made | When United States is selected → State/Province field should be a dropdown listing all U.S. states. When Palestine is selected → State/Province field should switch to a manual text input field | The system should not accept the invalid inputs and display an error note | The system should display a note under the field indicating "not valid inputs" | The system should display an appropriate error message | The system should display an error message and should stop proceeding to save the entry | The system should display an error message if the issue date is equal to or after the current date | The system should not accept the entry and should display an error message indicating the allowed characters | The system should not accept the entry and should display an error message indicating the allowed characters | The system should not accept the entry and should display an error message indicating "Revise the date – future dates are not allowed" | The system should delete the desired "Education" entry | The system should delete all the selected "education " entries | The system should not accept the entry and should display an error message indicating the allowed characters | The system should not accept the entry and should display an error message indicating the allowed characters | The system should not accept the entry and should display an error message indicating the allowed characters | The system should not accept the entry and should display an error message indicating the allowed characters | The system should not accept the entry and should display an error message indicating the allowed characters | The system should not accept the entry and should display an error message indicating "Revise the date – future dates are not allowed" | The system should not accept the entry and should display an error message indicating the allowed characters | The system should not accept the entry and should display an error message indicating "Revise the date – future dates are not allowed"
| Actual result | During the first login, The user is not redirected to the personal details screen | The system displays a successfully updated message when no changes have been made | the State/Province field does not switched correctly between dropdown and text input | The system accepts the invalid inputs and does not display an error note | The system accepts the invalid inputs without any rejection note | The system accepts the invalid inputs without any rejection note and display it | The system accepts the invalid inputs without any rejection note and save the entry | The system accepts the invalid input and proceeds save the document | The system should not accept the entry and should display an error message indicating the allowed characters | The system accepts the invalid input and proceeds save the document | The system accepts the invalid input and proceeds save the entry | The system does not delete the education entry and display an erroe messgae indicating"Records not found" | The system does not delete entries and displays an error message indicating"records are not found" | The system accepts the invalid input and proceeds save the entry | The system accepts the invalid input and proceeds save the entry | The system accepts the invalid input and proceeds save the entry | The system accepts the invalid input and proceeds save the entry | The system accepts the invalid input and proceeds save the entry | The system accepts the invalid input and proceeds save the entry | The system accepts the invalid input and proceeds save the entry | The system accepts the invalid input and proceeds save the entry
Bug tracking | Severity | Severity 4 "Low" | Severity 2 High | Severity 3 | Severity 3 | Severity 3 | Severity 2 | Severity 2 | Severity 2 | Severity 3 | Severity 3 | Severity 2 | Severity 2 | Severity 3 | Severity 2 | Severity 2 | Severity 2 | Severity 2 | Severity 2 | Severity 3 | Severity 2 | Severity 2
| Assigned to | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi | Areej Alashi
| Priority | Low | High | Medium | High | High | High | High | High | Medium | Medium | High | High | Medium | High | High | High | High | High | Medium | High | High
Notes | Bug Status | Deferred | New | New | New | New | open | New | Open | New | New | Open | Open | Open | New | New | Non-reproducible bug | New | Open | New | Open | Open

## Screenshots
Bug.01 | Bug .02
First attempt log in/ Info screen not displayed first | personal information saving with a blank fields
Bug.03 | Bug.04
State/Provice not switching | the City/Town field accepts invalid inputs
Bug.05 | Bug.06
Zip Code Field bug | Date of Birth Field bug
Bug.07 | Bug.08
Name Field bug | Issue Date Field bug
Bug.09 | Bug.10
Company Name Field bug | Job Title Field bug
Bug.11 | Bug.12
From/To Work Experience Date bug | Deleting an Education entry bug
Bug.13 | Bug.14
Deleting Multible Education entry bug | The ‘Major/Specialization’ field bug
Bug.15 | Bug.21
The ‘Institution’ Field bug | The Issue/Expiry date field bug
Bug.17 | Bug.18
The Year fied format bug | GPA/Score field bug
Bug.19 | Bug.20
Start/End date fields bug | License Number field bug